Below is a simple classroom example connecting Stories, Estimation, Velocity, and Slack.

# 🍔 Example: Food Delivery App (Iteration Planning)

“Our team is building a Food Delivery App like Swiggy or Zomato.”

# 1️⃣ User Stories

Write on board:

| Story | Description |
| --- | --- |
| Login | User logs into the app |
| View restaurants | User can see nearby restaurants |
| Add to cart | User adds food items |
| Online payment | User pays for order |
| Track delivery | User tracks order location |

Example story format:

"As a customer, I want to view restaurants so that I can order food."

Explain:

Stories must represent customer value.

# 2️⃣ Estimation (Story Points)

Developers estimate effort.

| Story | Points | Reason |
| --- | --- | --- |
| Login | 3 | Simple UI + authentication |
| View restaurants | 5 | Database + filtering |
| Add to cart | 5 | Session management |
| Online payment | 8 | Payment gateway integration |
| Track delivery | 5 | GPS integration |

Explain:

Points represent effort and complexity, not exact time.

# 3️⃣ Velocity

Say:

Last iteration the team completed:

Login (3)
View restaurants (5)
Add to cart (5)

Velocity =

3 + 5 + 5 = 13 points

Write:

Team Velocity = 13 points

# 4️⃣ Selecting Stories for Next Iteration

Ask students:

Which stories should we take if velocity = 13?

Options:

| Story | Points |
| --- | --- |
| Online payment | 8 |
| Track delivery | 5 |
| Ratings | 3 |

Students will see:

8 + 5 = 13

So iteration stories:

✔ Online payment
✔ Track delivery

# 5️⃣ Slack Example

Explain:

We should not plan exactly 13.

Slack ≈ 10% buffer

10% of 13 ≈ 1 point

So we plan about 12 points of work.

Remaining time used for:

• Fixing unexpected bugs
• Refactoring messy code
• Research on payment API

# 6️⃣ Shock Absorber Example

Tell students:

Suppose:

⚠ Payment API integration takes longer
⚠ Server issue occurs

Slack helps absorb the delay.

Without slack → iteration fails.

SUMMARY:

Stories → What users want

Estimation → Effort required

Velocity → Team capacity

Slack → Safety buffer