Slack:

In Extreme Programming (XP), slack is the practice of adding a safety buffer to iteration plans to ensure the team can consistently deliver on its commitments despite the inherent randomness of software development problems. Rather than scheduling the team to 100% capacity with story work, slack incorporates useful but non-urgent tasks that can be set aside if an emergency arises.

Here is a detailed breakdown of the practice based on the sources:

### 1. The Core Purpose: Protecting Commitments

Software projects are often disrupted by unpredictable events like illness, hardware failures, or late-breaking requirements.

- Stabilizing Velocity: While velocity accounts for a team’s average throughput, slack accounts for the randomness of disruptions. If a team's velocity fluctuates wildly, they likely need more slack.

- Reliability: By including slack, the team ensures that their promise to stakeholders—delivering specific stories by the iteration deadline—remains rock-solid.

### 2. Primary Slack Activities

Teams do not spend slack time doing nothing; they perform work that increases long-term productivity but can be postponed if the iteration commitment is at risk:

- Paying Down Technical Debt (Refactoring): Programmers spend time cleaning up existing code that has become messy or difficult to maintain. A good rule of thumb is to dedicate roughly 10% of the iteration (about half a day per week) to this activity. Developers should focus on refactorings that make their current work easier rather than speculating on future needs.

- Research Time: Teams set aside a specific block of time—often half a day per week—for programmers to conduct self-directed research on any topic of their choice. This encourages learning, prevents tunnel vision, and often leads to breakthroughs that benefit the project.

### 3. Managing Risks: The "Shock Absorber" Effect

When an iteration falls behind schedule, the team uses slack as a buffer to recover time:

- Refactoring as a Shock Absorber: If the iteration is going smoothly, pairs spend extra time refactoring; if it is rocky, they set aside non-critical refactoring to focus on story completion.

- Voluntary Overtime: If a small problem sneaks past the refactoring buffer, individuals may contribute an hour or two of voluntary overtime, though this should be rare.

- Cancelling Research Time: For larger problems, the team may cancel the scheduled research time for that week.

### 4. Boundaries and Warning Signs

The sources emphasize that slack must be used responsibly to avoid hiding systemic issues:

- Don't Cross the Line: If a team finds they must cancel research time or skip refactoring for two or three iterations in a row, they have overcommitted. In this case, the "slack" is actually required time, and the team should reduce their velocity to restore the buffer.

- Never Incur Technical Debt: Slack should never be gained by skipping essential quality practices like Test-Driven Development (TDD) or Pair Programming. Doing so meeting the current commitment at the expense of all future iterations.

### 5. Alternatives to Standard Slack

If a team prefers different non-urgent tasks, they can use:

- Reading Groups: Replacing research time with a collective session to read and discuss technical books or articles.

- Silver Stories: Scheduling low-priority stories that can be dropped if time runs out. However, this is discouraged because dropping a half-finished story leaves behind "half-done code" as technical debt.

### 6. Reducing the Need for Slack

Teams can eventually reduce the amount of slack they need by addressing the root causes of randomness:

- Improving Customer Availability: Ensuring on-site customers are available to answer questions immediately prevents programmers from waiting for information.

- Lowering Technical Debt: Cleaner code creates a more predictable environment, which reduces the number of "unexpected technical delays" during an iteration.

Stories:

In Extreme Programming (XP), stories are simple descriptions of work that serve as the primary line items in a project’s plan. Rather than being exhaustive requirements, they are "promissory notes for future conversation," used to facilitate communication between the team and stakeholders.

### Core Characteristics of a Story

A well-written story must possess two essential traits:

- Customer Value: Stories must be written in the customer’s terminology and describe an end-result they care about. Technical tasks (like "creating a build script") are not stories because customers cannot easily prioritize them; instead, these costs are bundled into the estimates for customer-valued stories.

- Clear Completion Criteria: There must be an objective test that allows the team to know exactly when the story is finished.

### The Use of Physical Story Cards

XP emphasizes writing stories on physical 3x5-inch index cards. The sources argue that physical cards are more effective than software tools for several reasons:

- Tactility: During release planning, team members can physically move cards around a table to visualize priorities and scope.

- Informative Workspace: Cards are posted on "Big Visible Charts" (the release and iteration boards), providing up-to-the-minute status updates to anyone in the room.

- Responsiveness: If a stakeholder has a new idea, the team can immediately help them write it on a card and discuss its place in the plan, which builds significant trust.

### Sizing and Splitting Stories

Stories should typically represent one or two days of work. A general rule is to size them so that the team can complete 4 to 10 stories per iteration.

- Splitting: If a story is too large, it should be broken down into "vertical stripes"—smaller, independent pieces of functionality that provide value on their own (e.g., "Process shipping address" instead of "Build database").

- Combining: Very small stories should be stapled together and estimated as a single unit.

### Special Types of Stories

Beyond standard feature requests, teams use special categories for other types of work:

- Documentation Stories: Used for work like user manuals that provide business value.

- Nonfunctional Stories: Address performance, scalability, or stability with quantifiable completion criteria.

- Bug Stories: Used to schedule significant defects that were not caught before a story was marked "done done".

- Spike Stories: Used for technical research when programmers do not know enough to estimate a real story.

### The "Done Done" Discipline

A story is only considered finished when it is "done done," meaning it is production-ready. This includes being tested, coded, refactored, integrated, and accepted by the customer. If a story is not 100% complete by the end of an iteration, the team receives zero credit for it when calculating velocity to ensure plans remain realistic.

Estimating:

In Extreme Programming (XP), estimating is a practice that focuses on identifying the effort required to complete a task rather than trying to predict its calendar duration. The goal is to provide reliable numbers that allow the team to balance their workload and predict release dates through a feedback mechanism called velocity.

### The Core Concept: Ideal Time

Programmers often struggle with traditional estimation because they cannot predict interruptions like meetings or emails. To solve this, XP uses ideal engineering days (also called story points):

- Definition: The amount of time a task would take if a programmer had perfect focus, zero interruptions, and all necessary resources at hand.

- Consistency over Accuracy: Individual estimates are rarely accurate, but experts naturally make consistent estimates. As long as the team is consistent in how they estimate, the scaling factor of velocity will correct the "inaccuracy" to match reality.

### Balancing Workload with Velocity

Velocity is the total number of story points a team completes in a single iteration. It serves as a vital feedback loop:

- Self-Correction: If a team underestimates their work, they won't finish all stories; this causes their velocity to drop, which automatically reduces the amount of work they sign up for in the next iteration.

- The "Done Done" Rule: Only stories that are 100% complete ("done done") at the end of an iteration count toward velocity; partial credit is never given.

- Stability: Velocity typically stabilizes after three or four iterations, providing a rock-solid basis for long-term commitments.

### How to Estimate Stories

Story estimation occurs with the Whole Team, where programmers provide the cost and customers provide the requirements.

- The Process: Programmers imagine the engineering tasks needed for a story and ask customers clarifying questions. One person suggests a number, and the group discusses it until they reach consensus.

- Handling Uncertainty: If a story is too complex to estimate, it is marked as a "Spike" for research, or "??" if customer details are missing.

- Sizing: Stories should be sized so the team can complete 4 to 10 per iteration.

### Estimating Iteration Tasks

While stories are estimated in ideal days for release planning, the specific technical tasks within an iteration are estimated in ideal hours.

- Each task should represent one to three hours of actual work for a pair (or two to six hours of effort).

- Estimating these tasks helps the team ensure their weekly plan is achievable and contains enough slack to handle surprises.

### Dealing with Pressure and Difficulty

- Slow Estimation: If a story takes longer than five minutes to estimate, it usually means customers are unprepared or programmers are diving too deep into design. The team should move on and come back to it later.

- "Why does this cost so much?": When stakeholders question estimates, programmers should respond with technical options and scope-reduction alternatives rather than defensive arguments.

- Refusing Changes: Programmers must be professional and refuse to lower an estimate simply because of schedule pressure. If the estimate is truly too high, velocity will naturally increase to compensate.